## Register
id | name | type | marks | effort_days | lead_time_days | external | start_by | finish_by | slack_days | depends_on | owner | notes
category_analysis | Category and competitor comms audit (feeds concept, strategy and media) | scored | 0 | 3 | 0 | no | 2026-08-25 | 2026-08-28 | -2 |  | Khalid Naseem | Carries no marks itself but feeds 55. Use the competitor-comms-audit skill; capture sheet already generated at workspace/audit/capture.xlsx.
entity_decision | Decide which Group entity applies (must itself hold APNS/PBA/AAP/PID) | gate | 0 | 1 | 0 | no | 2026-08-26 | 2026-08-27 | -1 |  | Faheem Ahmed | ITA 22.1/23.3 exclude parents, subsidiaries and affiliates; PDS caps JV members at nil. Synite Digital is the digital practice and is unlikely to hold press/broadcast accreditation - probably Synergy Advertising. Blocks everything else.
bank_cert | Bank certificate of financial stability | gate | 0 | 1 | 4 | yes | 2026-08-27 | 2026-09-01 | 0 | entity_decision | Finance | Not held. Bank turnaround is the risk, not our effort.
campaign_concept | Campaign Concept | scored | 15 | 2 | 0 | no | 2026-08-28 | 2026-08-30 | 1 | concept_develop, concept_core_idea, concept_relevance, concept_rationale | Ferrukh Syed | Task breakdown from data/SLIC Doc.docx (internal checklist, 2026-08-27).
accreditation | APNS, PBA and AAP registration certificates plus PID enlistment | gate | 3 | 1 | 3 | yes | 2026-08-28 | 2026-09-01 | 1 | entity_decision | Compliance | Pass/fail eligibility AND 3 marks. Not evidenced in any prior submission.
clarification | File clarification with SLIC on EPADS (missing Schedule of Requirements / campaign brief) | gate | 0 | 1 | 2 | yes | 2026-08-28 | 2026-08-31 | 1 |  | Emaad Ishaq Khan | Window closes 31 Aug (ITA 7.1). Also check the portal Lots section first.
not_blacklisted | Non-blacklisting certificate from APNS and PBA | gate | 0 | 1 | 3 | yes | 2026-08-28 | 2026-09-01 | 1 | entity_decision | Compliance
slic_dues | Certificate that newspaper bills released by State Life are cleared | gate | 0 | 1 | 3 | yes | 2026-08-28 | 2026-09-01 | 1 | entity_decision | Finance | Check with accounts whether we have ever been released by State Life.
comp_competitors | Identify relevant competitors | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | category_analysis | Khalid Naseem | brands.csv already lists 16 across four rings - confirm the frame, do not rebuild it.
comp_analyse_comms | Analyse competitor communication | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | comp_competitors | Khalid Naseem | Coding pass on capture.xlsx. Every row needs a source_url or analyze_audit.py drops it.
comp_gaps | Identify gaps and opportunities | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | comp_analyse_comms | Khalid Naseem | The claim x register crosstab; white space is the output campaign_concept consumes.
comp_differentiation | Establish SLIC's potential communication differentiation | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | comp_gaps | Khalid Naseem | The handover line to the concept. If this can be deleted without weakening the concept, the whole 15-mark section has failed.
concept_develop | Develop campaign concept | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | comp_differentiation | Ferrukh Syed
concept_core_idea | Clearly articulate the core idea | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | concept_develop | Ferrukh Syed
concept_relevance | Ensure concept is relevant to SLIC | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | concept_core_idea | Ferrukh Syed | Relevance to which product line is exactly what the missing Section VII would have told us. Until the clarification lands this is an assumption we must state on the page.
concept_rationale | Prepare presentation-ready rationale | informational | 0 | 0 | 0 | no | 2026-08-28 | 2026-08-28 | 1 | concept_relevance | Ferrukh Syed | Presentation-ready is the team's own assumption - the tender sets no format or page limit. Confirm whether a deck is expected or whether it came from the EPADS Lots.
revenue | Audited accounts evidencing PKR 100m+ aggregate revenue over three years | scored | 4 | 1 | 2 | yes | 2026-08-29 | 2026-09-01 | 2 | entity_decision | Finance | Entity-level, not Group. Confirm the applicant entity clears the threshold.
staff_annexure | Annexure III staff particulars with CVs | scored | 3 | 2 | 0 | no | 2026-08-29 | 2026-08-31 | 2 | entity_decision | HR | UNICEF bid has 11 bios and CVs - recast into SLIC columns and extend.
tax_cert | Income tax / GST certificate, NTN and 2023-25 returns, attested | gate | 2 | 1 | 2 | yes | 2026-08-29 | 2026-09-01 | 2 | entity_decision | Finance | Annexed to the UNICEF bid; needs entity-level version plus attestation.
communication_strategy | Communication Strategy | scored | 15 | 1 | 0 | no | 2026-08-30 | 2026-08-31 | 3 | strat_objective, strat_audience, strat_approach, strat_messaging, strat_journey | Khalid Naseem | Task breakdown from data/SLIC Doc.docx (internal checklist, 2026-08-27).
creative_artworks | Creative Artworks | scored | 15 | 2 | 0 | no | 2026-08-30 | 2026-09-01 | 3 | art_kv_direction, art_samples, art_quality, art_demonstrates_concept | Ferrukh Syed | Task breakdown from data/SLIC Doc.docx (internal checklist, 2026-08-27).
headcount | Permanent headcount evidence (payroll / EOBI) for 20+ employees | scored | 4 | 1 | 1 | no | 2026-08-30 | 2026-09-01 | 3 | entity_decision | HR
clean_record | Rs.100 stamp-paper declaration per Annexure II | scored | 3 | 1 | 1 | yes | 2026-08-30 | 2026-09-01 | 3 | entity_decision | Compliance | Stamp paper and notarisation are the lead time. Form emitted by slic-pq build.
secp | SECP incorporation certificate, Memorandum and Articles, attested | scored | 2 | 1 | 1 | yes | 2026-08-30 | 2026-09-01 | 3 | entity_decision | Company Secretary
offices | Evidence of operational offices in Karachi, Lahore and Islamabad | scored | 2 | 1 | 1 | no | 2026-08-30 | 2026-09-01 | 3 | entity_decision | Admin | Entity-level leases or utility bills. Affiliate offices do not count.
strat_objective | Define communication objective | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | category_analysis | Khalid Naseem
strat_audience | Define target audience | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | strat_objective | Khalid Naseem | Blocked on the same clarification as concept_relevance - no segment is stated anywhere.
strat_approach | Establish communication approach | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | strat_audience | Khalid Naseem
strat_messaging | Develop messaging direction | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | strat_approach | Khalid Naseem
strat_journey | Define communication journey | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | strat_messaging | Khalid Naseem
art_kv_direction | Develop KV / creative direction | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | campaign_concept | Ferrukh Syed
art_samples | Prepare required sample artworks | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | art_kv_direction | Ferrukh Syed | Required is undefined - no count or format is given. Weight to press and broadcast: the criteria gate on APNS/PBA/PID and ask for print ads and TVC/DVC as evidence.
art_quality | Ensure quality is presentation-ready | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | art_samples | Ferrukh Syed
art_demonstrates_concept | Ensure creative work demonstrates the proposed campaign concept | informational | 0 | 0 | 0 | no | 2026-08-30 | 2026-08-30 | 3 | art_quality | Ferrukh Syed
competitive_analysis | Competitive Analysis section | scored | 15 | 1 | 0 | no | 2026-08-31 | 2026-09-01 | 4 | comp_competitors, comp_analyse_comms, comp_gaps, comp_differentiation | Khalid Naseem | Task breakdown from data/SLIC Doc.docx (internal checklist, 2026-08-27).
media_mix | Proposed Media Mix | scored | 10 | 1 | 0 | no | 2026-08-31 | 2026-09-01 | 4 | media_channels, media_roles, media_supports_strategy | Suhira Munshi | Task breakdown from data/SLIC Doc.docx (internal checklist, 2026-08-27). No budget is stated in the tender - budget logic must be presented as indicative.
campaign_experience | Three years of campaign evidence - print, TVC/DVC, transmission certificates | scored | 3 | 1 | 0 | no | 2026-08-31 | 2026-09-01 | 4 |  | Ferrukh Syed | Lead with ATL (Polio docu-dramas, SBP anthems) given the APNS/PBA framing.
expertise | CVs evidencing art direction, creative direction, copywriting, account management | scored | 2 | 1 | 0 | no | 2026-08-31 | 2026-09-01 | 4 | staff_annexure | HR
client_list | Five-year client list with services, plus active-client evidence | scored | 2 | 1 | 0 | no | 2026-08-31 | 2026-09-01 | 4 |  | Emaad Ishaq Khan | UNICEF S2.4/S2.6 is the source. Confirm disclosure permissions.
profile | Agency profile - addresses, branches, year of establishment | gate | 0 | 1 | 0 | no | 2026-08-31 | 2026-09-01 | 4 | entity_decision | Emaad Ishaq Khan
media_channels | Define proposed media channels | informational | 0 | 0 | 0 | no | 2026-08-31 | 2026-08-31 | 4 | category_analysis | Suhira Munshi
media_roles | Explain role of each medium | informational | 0 | 0 | 0 | no | 2026-08-31 | 2026-08-31 | 4 | media_channels | Suhira Munshi
media_supports_strategy | Demonstrate how the media mix supports the communication strategy | informational | 0 | 0 | 0 | no | 2026-08-31 | 2026-08-31 | 4 | media_roles, communication_strategy | Suhira Munshi | Depends on the strategy landing, not just the category read - the internal doc makes this an explicit test.
assembly | Assemble, proof, attest and upload to EPADS | gate | 0 | 1 | 0 | no | 2026-09-01 | 2026-09-02 | 5 | accreditation, bank_cert, not_blacklisted, slic_dues, tax_cert, secp, clean_record, revenue, headcount, offices, staff_annexure, expertise, client_list, campaign_experience, profile, competitive_analysis, campaign_concept, communication_strategy, creative_artworks, media_mix | Emaad Ishaq Khan | Portal uploads fail. Do not leave this to the morning of the 3rd.